## Sheet1
SI.No | DATE | TIME | ACITIVITY TITLE | ACTIVITY DSECRIPTION | #ERROR | ERROR DETAILS | ERROR FIXED | STATUS ACTIVITY | DEADLINE
1 | 12.11.2020 | 5.00Pm | ProjectStructure | Created Required pacakges with respective class and Database Structure |  |  |  | Completed
2 | 18.11.2020 | 1.15Pm | Getters & Setters | Completed all coding of 5 model classes |  |  |  | Completed
3 | 18.11.2020 | 4.30Pm | JDBC Connectivity | Established JDBC connection |  |  |  | Completed
4 | 19.11.2020 | 1.10Pm | Inserting methods | Created Insert data methods for all the classes |  |  |  | Completed
5 | 20.11.2020 | 3.00Pm | Testing get and set methods | Connected with Database and inserted and retrived data | NullPointerException | Inserted data was not captured by database or inseted null values | Made changes in get and set methods | Completed
6 | 21.11.2020 | 1.30Pm | Functions Implementation | Implemented all 5 functions for all packages |  |  |  | Completed
7 | 22.11.2020 | 6.00Pm | Task Implementation_1 | Implemented operations or tasks to Employee |  |  |  | Completed
8 | 23.11.2020 | 5.00Pm | Task Implementation_2 | Implemented operations or tasks to Skill |  |  |  | Completed
9 | 24.11.2020 | 9.00Pm | Task Implementation_3 | Implemented operations or tasks to Job and EmpJob |  |  |  | Completed
10 | 25.11.2020 | 10.00Am | Task Implementation_4 | Implemented operations or tasks to EmpSkill |  |  |  | Completed
11 | 26.11.2020 | 2.00Pm | Controll Creation | Created Controll methods for Employee,Skill,Job Packages |  |  |  | Completed
12 | 27.11.2020 | 10.00Am | Testing Controll methods | Tested various tasks via controll method |  |  |  | Completed
13 | 28.11.2020 | 12.00Pm | Creation of View Package | Created View of HRA,PME and EMP |  |  |  | Completed
14 | 29.11.2020 | 10.00Am | Login Frame | Created Login Frame and tested |  |  |  | Completed
15 | 29.11.2020 | 7.00Pm | Registration Frame | Created and implemented Registartion Frame |  |  |  | Completed
16 | 30.11.2020 | 10.00Am | HRA Frame | Implemented some of the HR operations |  |  |  | Completed
17 | 1.12.2020 | 9.00Pm | HRA Frame | Implemented all the operations |  |  |  | Completed
18 | 2.12.2020 | 5.00Pm | HRA Frame | Tested the implemented operations one by one |  |  |  | Completed
19 | 3.12.2020 | 10.00Am | EMP Frame | Created Frame design
20 | 4.12.2020 | 7.00Pm | EMP Frame | Implemeting operations one by one
21 | 5.12.2020 | 10.00Am | EMP Frame | Implementattion of tasks
22 | 7.12.2020 | 7.00Pm | PME Frame | Created Frame design